## Sheet1
Requirement | Task | Member | Describe | Done | Percent complete
| Use case diagram | Nguyễn Thành Đạt | Draw use case diagram | Y | 100%
Functional requirement
| Non-functional requirement | Nguyễn Thành Đạt | List and detail non-functional requirement | Y | 100%
| Functional diagram | Nguyễn Thành Đạt | Draw Functional diagram | Y | 100%
| UML sequence diagram | Nguyễn Thành Đạt | Draw UML sequence diagram | Y | 100%
| List function | Võ Đăng Phước | Suggest function to code | Y | 80%
Sign
| Describe system | Võ Đăng Phước
| Require | Trần Hữu Phát | UI require / Other require | Y | 100%
Test | Testcase file | Nguyễn Quốc Khánh | Write a file to check all possible input | Y | 100%
Design
| List friend | Nguyễn Thành Đạt | Design partern | Y | 100%
| Upcoming your friend birthday | Nguyễn Thành Đạt | Design partern | Y | 100%
| Add friend | Nguyễn Thành Đạt | Design partern | Y | 100%
| UTA | Trần Hữu Phát | Design partern | Y | 100%
Code | List friend layout | Nguyễn Thành Đạt | Code xml file to design layout follow design | Y | 100%
| Add friend layout | Nguyễn Thành Đạt | Code xml file to design layout follow design | Y | 100%
| Upcoming your friend birthday layout | Nguyễn Thành Đạt | Code xml file to design layout follow design | Y | 100%
| MainActivity | Nguyễn Anh Hào | Show the friend list, show who's birthday is coming | Y | 100%
| activity_add_new_friend | Nguyễn Anh Hào | take input and send into main | Y | 100%
| Object Date | Nguyễn Anh Hào | Have day/month/year of a person | Y | 100%
| Object Friend | Nguyễn Anh Hào | Have Date, Friend, sex | Y | 100%
| Object Person | Nguyễn Anh Hào | Have first name, middle name, last name | Y | 100%
| dialog_upcoming_friend | Nguyễn Anh Hào | Show who's birthday is coming | N | 50%
| Demo code | Trần Hữu Phát | Code Java and XML in Android Studio | Y | 100%