## Sheet1
Requirement | Tasklist | Member | Describe | Done | Percent complete | Date receiver | Deadline
| Use case diagram | Nguyễn Thành Đạt | Draw use case diagram | Y | 100% | 2018-10-12 | 14/12/2018
| Functional requirement | Nguyễn Anh Hào | List and detail functional requirement | Y | 100% | 20/12/2018 | 22/12/2018
| Non-functional requirement | Nguyễn Thành Đạt | List and detail non-functional requirement | Y | 100% | 24/12/2018 | 24/12/2018
| Functional diagram | Nguyễn Thành Đạt | Draw Functional diagram | Y | 100% | 24/12/2018 | 24/12/2018
| UML sequence diagram | Nguyễn Thành Đạt | Draw UML sequence diagram | Y | 100% | 24/12/2018 | 24/12/2018
| List function | Võ Đăng Phước | Suggest function to code | Y | 80% | 15/12/2018 | 23/12/2018
| Sign | Nguyễn Quốc Khánh | Log in | Y | 100% | 18/12/2018 | 21/12/2018
| Describe system | Võ Đăng Phước | complain system | Y | 100% | 17/12/2018 | 24/12/2018
| Require | Trần Hữu Phát | UI require / Other require | Y | 100% | 20/12/2018 | 24/12/2018
Test | test layout | Nguyễn Quốc Khánh | input data in layout and check , then output to file excel | Y | 100%
| build test code | Nguyễn Anh Hào | build construction code test | Y | 100%
| test case 1 | Nguyễn Thành Đạt | code test case 1 | Y | 100%
| test case 2 | Võ Đăng Phước | code test case 2 | Y | 100%
| test case 3 | Trần Hữu Phát | code test case 3 | Y | 100%
Design
| List friend | Nguyễn Thành Đạt | Design partern | Y | 100%
| Upcoming your friend birthday | Nguyễn Thành Đạt | Design partern | Y | 100%
| Add friend | Nguyễn Thành Đạt | Design partern | Y | 100%
| UTA | Trần Hữu Phát | Design partern | Y | 100%
| Log in | Võ Đăng Phước | Design partern | Y | 100%
| Register | Nguyễn Anh Hào | Design partern | Y | 100%
| Profile | Nguyễn Quốc Khánh | Design partern | Y | 100%
Code | List friend layout | Nguyễn Thành Đạt | Code xml file to design layout follow design | Y | 100%
| Add friend layout | Nguyễn Thành Đạt | Code xml file to design layout follow design | Y | 100%
| Upcoming your friend birthday layout | Nguyễn Thành Đạt | Code xml file to design layout follow design | Y | 100%
| MainActivity | Nguyễn Anh Hào | Show the friend list, show who's birthday is coming | Y | 100%
| activity_add_new_friend | Nguyễn Anh Hào | take input and send into main | Y | 100%
| Object Date | Nguyễn Anh Hào | Have day/month/year of a person | Y | 100%
| Object Friend | Nguyễn Anh Hào | Have Date, Friend, sex | Y | 100%
| Object Person | Nguyễn Anh Hào | Have first name, middle name, last name | Y | 100%
| dialog_upcoming_friend | Nguyễn Anh Hào | Show who's birthday is coming | N | 50%
| Demo code | Trần Hữu Phát | Code Java and XML in Android Studio | Y | 100%